## Sheet1
ID | Task Description | Predecessors | Duration | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13
1 | Identify requirements in detail | —— | 1 day
2 | Establishing groups & tasks | 1 | 1 day
3 | Field trip | 2 | 1 day
4 | Initial design & notebook | 1，2，3 | 2 days
5 | Purchasing the materials | 1，2 | 2 days
6 | Build the basic model of car | 4，5 | 4 days
7 | Determine the Line-tracking methdology | 4，5 | 6 days
8 | Programming for motivated car | 6 | 8 days
9 | Programming for Line-tracking | 7 | 8 days
10 | Programming for Color recognition | 6，7 | 9 days
11 | Combine the two major tasks | 6，7 | 7 days
12 | Test & Ameliorate | 10 | 15 days
13 | Finishing the report & Video | 11 | 5 days
Yellow means tasks have been finished
Red mesns tasks timetable have been decided
Blue means tasks timetable may change due to some circumstance